## Start Here
Lien Waiver Tracker
Free template from lienwaivertracker.com. Track every waiver, every pay app, every sub.
How to use it
1. Settings tab: add your company name and project names. Change "Overdue after (days)" if you like.
2. Waiver Log tab: add one row for every waiver you need. Usually that is one conditional waiver per sub per pay app, plus the matching unconditional after payment.
3. Fill in Date Requested when you ask for the waiver, Date Received when it comes back, and Date Paid when you release payment.
4. Status, Days Outstanding and Payment Check calculate automatically. Red means act now.
5. Dashboard tab: totals and a per-project view of what is outstanding, overdue, or paid without a waiver.
Legend
Blue text on light-yellow cells = your inputs. Black text = formulas. Do not type over the formulas.
Rows 5–8 of the Waiver Log are EXAMPLE rows showing each status. Overwrite or delete them.
What the Payment Check column means
Hold payment: the conditional waiver for this payment has not been received yet.
Paid without waiver: payment was released before the conditional waiver arrived. This is your lien exposure.
Received after payment: the conditional waiver arrived, but after you paid.
Collect now: payment is out, so request the unconditional waiver for it.
After payment: unconditional waiver not due until you release this payment.
Want it to chase subs for you?
The Autopilot version sends waiver requests and reminders by email and flags payments to hold: lienwaivertracker.com/autopilot
Not legal advice. Waiver rules differ by state, and several states (including California, Texas, Arizona and Georgia) require specific statutory waiver forms. Use the correct form for your state and ask a construction attorney when in doubt.

## Waiver Log
Waiver Log
Project | Pay App / Invoice # | Party (sub or supplier) | Tier | Contact email | Waiver type | Through date | Payment amount ($) | Date requested | Date received | Date paid | Status | Days outstanding | Payment check | Notes
Maple St Remodel | PA-03 | Apex Electric LLC | Subcontractor | billing@apex-electric.example | Conditional Progress | 2026-08-31 | 18500 | 2026-09-02 | 2026-09-05 | 2026-09-10 |  |  |  | Pay app 3 approved
Maple St Remodel | PA-02 | Apex Electric LLC | Subcontractor | billing@apex-electric.example | Unconditional Progress | 2026-07-31 | 12000 | 2026-09-02 |  | 2026-08-12 |  |  |  | Lagging unconditional for PA-02
Oak Ave Addition | PA-01 | Ridgeline Plumbing Inc | Subcontractor | office@ridgeline-plumbing.example | Conditional Progress | 2026-09-15 | 9750
Oak Ave Addition | PA-01 | BuildMart Supply | Supplier | ar@buildmart.example | Conditional Progress | 2026-09-15 | 4200 | 2026-09-18 |  | 2026-09-19 |  |  |  | Paid early, chase waiver
Note on L4: Calculated. Not requested / Requested / Overdue / Received. Overdue threshold is on the Settings tab.
Note on N4: Calculated. Compares waiver type, received date and paid date. See Start Here for meanings.

## Dashboard
Dashboard
Totals
Waivers tracked
Received
Outstanding (requested, not back)
Overdue
Not yet requested
Payments released without conditional waiver
Amount paid without conditional waiver ($)
Payments to hold until waiver arrives ($)
Unconditional waivers to collect now
By project
Project | Tracked | Received | Outstanding | Overdue | Paid without waiver | $ to hold

## Settings
Settings
Edit the yellow cells. Lists below feed the dropdowns on the Waiver Log.
Company name | Your Company LLC
As-of date |  | Leave as =TODAY() or type a fixed date to review a past period.
Overdue after (days) | 7 | Requests older than this with no waiver back show as Overdue.
Projects |  | Waiver types | Party tier
Maple St Remodel |  | Conditional Progress | Subcontractor
Oak Ave Addition |  | Unconditional Progress | Sub-subcontractor
|  | Conditional Final | Supplier
|  | Unconditional Final | Equipment rental
Other

## Email Templates
Email Templates
Copy, paste and fill the [brackets]. The Autopilot version sends these for you automatically.
Waiver request
Subject: Lien waiver needed: [Project] – [Pay App #] Hi [Name], To release payment of $[Amount] for [Project], [Pay App #], we need a signed [Conditional Progress] lien waiver through [Through Date]. Please reply with the signed waiver by [Due Date]. Use your state's required form if your state has one. Payment is released once we receive it. Thanks, [Your Name] [Company]
Reminder (overdue)
Subject: Reminder: lien waiver still needed – [Project] – [Pay App #] Hi [Name], Following up on the [Waiver Type] lien waiver for [Project], [Pay App #] ($[Amount], through [Through Date]). We requested it on [Date Requested] and are holding payment until it arrives. Could you send it over today? Thanks, [Your Name]
Unconditional after payment
Subject: Unconditional lien waiver for payment sent – [Project] Hi [Name], Payment of $[Amount] for [Project], [Pay App #] was released on [Date Paid]. Please send the signed [Unconditional Progress / Final] lien waiver for that payment once funds have cleared. Thanks, [Your Name]